## Sheet1
USER STORY | TASKS | Start Time | Sprint no.1 Backlog | [13 empty] | Total Time
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As a user should be easy to navigate through project repositories | Setup web interface repositories | 20 | Sprint no.1 Backlog Day 1: 3; Sprint no.1 Backlog Day 2: 2; Sprint no.1 Backlog Day 3: 3; Sprint no.1 Backlog Day 4: 1; Sprint no.1 Backlog Day 5: 6; Sprint no.1 Backlog Day 12: 3; Sprint no.1 Backlog Day 13: 2 | 20
| Setup back-end server repositories | 10 | Sprint no.1 Backlog Day 1: 2; Sprint no.1 Backlog Day 2: 3; Sprint no.1 Backlog Day 3: 3; Sprint no.1 Backlog Day 4: 3 | 11
| Setup scraper repositories | 1 | Sprint no.1 Backlog Day 14: 3 | 3
| Setup integration repositories | 2 | Sprint no.1 Backlog Day 1: 2 | 2
| Updated integration repository | 1 | bar: Sprint no.1 Backlog Day 14
As a user I should be able to search for a location and load it | Implement auto complete | 20 | Sprint no.1 Backlog Day 6: 5; Sprint no.1 Backlog Day 7: 4; Sprint no.1 Backlog Day 8: 4; Sprint no.1 Backlog Day 9: 3; Sprint no.1 Backlog Day 10: 4
| Connect automplete to third party API | 3 | Sprint no.1 Backlog Day 7: 1; Sprint no.1 Backlog Day 8: 2
| Implement on select | 2 | bar: Sprint no.1 Backlog Day 9 to Sprint no.1 Backlog Day 10
| Reload map | 1 | [14 empty] | 1 | bar: Sprint no.1 Backlog Day 10
0
0
As a user I should be able to download disaster data from third party API | Configure RethinkDB | 2 | [14 empty] | 2 | bar: Sprint no.1 Backlog Day 5 to Sprint no.1 Backlog Day 6
| Create an express scrapper server | 3 | Sprint no.1 Backlog Day 4: 1; Sprint no.1 Backlog Day 7: 2 | 3
| Create a data model for RethinkDB | 2 | Sprint no.1 Backlog Day 8: 2 | 2
| Code the function to connect to the API | 4 | Sprint no.1 Backlog Day 4: 1; Sprint no.1 Backlog Day 9: 2; Sprint no.1 Backlog Day 10: 1 | 4
| Code function to download disaster JSON data | 24 | Sprint no.1 Backlog Day 6: 2; Sprint no.1 Backlog Day 8: 3; Sprint no.1 Backlog Day 10: 5; Sprint no.1 Backlog Day 11: 6; Sprint no.1 Backlog Day 12: 2; Sprint no.1 Backlog Day 13: 2 | 20
0
0
| Actual Remaining Hours | 95 | 88 | 83 | 77 | 71 | 64 | 56 | 49 | 38 | 32 | 20 | 14 | 9 | 5 | 1
| Estimated Remaining Hours | 95 | 88.2143 | 81.4286 | 74.6429 | 67.8571 | 61.0714 | 54.2857 | 47.5 | 40.7143 | 33.9286 | 27.1429 | 20.3571 | 13.5714 | 6.7857 | -1.5987e-14