## Sheet1
COEUS SCRUM MEETING ACTION ITEMS
Description | Reported By | Reported At | Assignee | Due By | open/closed
Cannot install some of the software required to complete tasks since my laptop is a 32 bit machine | Kamogelo Tswene | 29-06-2016 | Kamogelo Tswene | 05-06-2016 | open
Using SailsJS would set-us back because it was a new framework and required more time to learn | Keletso Molefe | 08-07-2016 | Nsovo Baloyi | 10-07-2016 | closed
Dificulty in locating disaster data from third party API | Maluleki Nyuswa | 12-07-2016 | Nsovo Baloyi | 30-07-2016 | open