## Sheet1
USER STORY | TASKS | Start Time | Sprint no.3 Backlog
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As a user should be easy to navigate through project repositories | Setup web interface repositories | 20 | Sprint no.3 Backlog Day 1: 3; Sprint no.3 Backlog Day 2: 2; Sprint no.3 Backlog Day 3: 3; Sprint no.3 Backlog Day 4: 1; Sprint no.3 Backlog Day 5: 6; Sprint no.3 Backlog Day 12: 3; Sprint no.3 Backlog Day 13: 2 | 20
| Setup back-end server repositories | 10 | Sprint no.3 Backlog Day 1: 2; Sprint no.3 Backlog Day 2: 3; Sprint no.3 Backlog Day 3: 3; Sprint no.3 Backlog Day 4: 3 | 11
| Setup scraper repositories | 1 | Sprint no.3 Backlog Day 14: 3 | 3
| Setup integration repositories | 2 | Sprint no.3 Backlog Day 1: 2 | 2
| Updated integration repository | 1 | [14 empty] | 1 | bar: Sprint no.3 Backlog Day 14
As a user I should be able to search for a location and load it | Implement auto complete | 20 | Sprint no.3 Backlog Day 6: 5; Sprint no.3 Backlog Day 7: 4; Sprint no.3 Backlog Day 8: 4; Sprint no.3 Backlog Day 9: 3; Sprint no.3 Backlog Day 10: 4 | 20
| Connect automplete to third party API | 3 | Sprint no.3 Backlog Day 7: 1; Sprint no.3 Backlog Day 8: 2 | 3
| Implement on select | 2 | [14 empty] | 2 | bar: Sprint no.3 Backlog Day 9 to Sprint no.3 Backlog Day 10
| Reload map | 1 | [14 empty] | 1 | bar: Sprint no.3 Backlog Day 10
As a user I should be able to view the weather of any location | Create component | 6 | Sprint no.3 Backlog Day 1: 3; Sprint no.3 Backlog Day 2: 1; Sprint no.3 Backlog Day 3: 2; Sprint no.3 Backlog Day 4: 1 | 7
| Create disaster service | 20 |  |  |  | 3 | 5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24
| Add mock objects | 5 | Sprint no.3 Backlog Day 7: 2; Sprint no.3 Backlog Day 8: 2; Sprint no.3 Backlog Day 10: 1; Sprint no.3 Backlog Day 11: 1 | 6
| Display information on map component | 20 | Sprint no.3 Backlog Day 9: 5; Sprint no.3 Backlog Day 10: 3; Sprint no.3 Backlog Day 11: 3; Sprint no.3 Backlog Day 12: 4; Sprint no.3 Backlog Day 13: 2; Sprint no.3 Backlog Day 14: 1 | 18
| Create disaster interface | 1 | Sprint no.3 Backlog Day 6: 2 | 2
0
0
As a user I should be able to view disasters for any location | Configure RethinkDB | 2 | Sprint no.3 Backlog Day 1: 2; Sprint no.3 Backlog Day 2: 1 | 3
| Create an express server | 10 | Sprint no.3 Backlog Day 1: 1; Sprint no.3 Backlog Day 2: 5; Sprint no.3 Backlog Day 3: 4; Sprint no.3 Backlog Day 4: 3 | 13
| Create a data model for RethinkDB | 4 | Sprint no.3 Backlog Day 5: 3; Sprint no.3 Backlog Day 6: 2 | 5
| Create routes | 8 | Sprint no.3 Backlog Day 5: 1; Sprint no.3 Backlog Day 6: 3; Sprint no.3 Backlog Day 7: 4 | 8
| Create controllers | 48 |  |  |  | 2 | 1 |  |  | 8 | 9 | 8 | 6 | 8 | 7 | 6 | 55
As a user I should be able to view the weather of any location | Create back-end service | 60 | Sprint no.3 Backlog Day 1: 3; Sprint no.3 Backlog Day 2: 1; Sprint no.3 Backlog Day 3: 2; Sprint no.3 Backlog Day 4: 1 | 7
| Created rest API on the front-end | 20 |  |  |  | 3 | 5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24
| Visualized daily focus | 20 | Sprint no.3 Backlog Day 7: 2; Sprint no.3 Backlog Day 8: 2; Sprint no.3 Backlog Day 10: 1; Sprint no.3 Backlog Day 11: 1 | 6
|  |  | Sprint no.3 Backlog Day 9: 5; Sprint no.3 Backlog Day 10: 3; Sprint no.3 Backlog Day 11: 3; Sprint no.3 Backlog Day 12: 4; Sprint no.3 Backlog Day 13: 2; Sprint no.3 Backlog Day 14: 1 | 18
|  |  | Sprint no.3 Backlog Day 6: 2 | 2
0
0
As a user I should be able to view disasters for any location | Create disaster service | 4 | Sprint no.3 Backlog Day 1: 2; Sprint no.3 Backlog Day 2: 3 | 5
| Integrated with back-end server | 2 | [14 empty] | 2 | bar: Sprint no.3 Backlog Day 3 to Sprint no.3 Backlog Day 4
| Visualize earthquake data using map service | 24 | Sprint no.3 Backlog Day 5: 5; Sprint no.3 Backlog Day 6: 6; Sprint no.3 Backlog Day 7: 5; Sprint no.3 Backlog Day 8: 6; Sprint no.3 Backlog Day 9: 5 | 27
| Visualize fire data using map service | 2 | Sprint no.3 Backlog Day 10: 2 | 2
| Impelemented data clustering | 20 | Sprint no.3 Backlog Day 11: 5; Sprint no.3 Backlog Day 12: 7; Sprint no.3 Backlog Day 13: 6; Sprint no.3 Backlog Day 14: 4 | 22
| Implemeted time series query | 3 | Sprint no.3 Backlog Day 10: 4 | 4
0
| Actual Remaining Hours | 339 | 321 | 305 | 290 | 272 | 246 | 226 | 204 | 176 | 144 | 112 | 89 | 59 | 36 | 16
| Estimated Remaining Hours | 339 | 314.7857 | 290.5714 | 266.3571 | 242.1429 | 217.9286 | 193.7143 | 169.5 | 145.2857 | 121.0714 | 96.8571 | 72.6429 | 48.4286 | 24.2143 | -9.2371e-14