## Sheet1
USER STORY | TASKS | Start Time | Sprint no.2 Backlog | [13 empty] | Total Time
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As a user I should be able to display disasters by type on the front end | Create component | 6 | Sprint no.2 Backlog Day 1: 3; Sprint no.2 Backlog Day 2: 1; Sprint no.2 Backlog Day 3: 2; Sprint no.2 Backlog Day 4: 1 | 7
| Create disaster service | 20 |  |  |  | 3 | 5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24
| Add mock objects | 5 | Sprint no.2 Backlog Day 7: 2; Sprint no.2 Backlog Day 8: 2; Sprint no.2 Backlog Day 10: 1; Sprint no.2 Backlog Day 11: 1 | 6
| Display information on map component | 20 | Sprint no.2 Backlog Day 9: 5; Sprint no.2 Backlog Day 10: 3; Sprint no.2 Backlog Day 11: 3; Sprint no.2 Backlog Day 12: 4; Sprint no.2 Backlog Day 13: 2; Sprint no.2 Backlog Day 14: 1 | 18
| Create disaster interface | 1 | Sprint no.2 Backlog Day 6: 2 | 2
0
0
As a user I should be able to get json data from database through the back-and sever | Configure RethinkDB | 2 | Sprint no.2 Backlog Day 1: 2; Sprint no.2 Backlog Day 2: 1 | 3
| Create an express server | 10 | Sprint no.2 Backlog Day 1: 1; Sprint no.2 Backlog Day 2: 5; Sprint no.2 Backlog Day 3: 4; Sprint no.2 Backlog Day 4: 3 | 13
| Create a data model for RethinkDB | 4 | Sprint no.2 Backlog Day 5: 3; Sprint no.2 Backlog Day 6: 2 | 5
| Create routes | 8 | Sprint no.2 Backlog Day 5: 1; Sprint no.2 Backlog Day 6: 3; Sprint no.2 Backlog Day 7: 4 | 8
| Create controllers | 48 |  |  |  | 2 | 1 |  |  | 8 | 9 | 8 | 6 | 8 | 7 | 6 | 55
0
0
| Actual Remaining Hours | 124 | 118 | 111 | 105 | 96 | 86 | 79 | 71 | 59 | 43 | 29 | 17 | 3 | -8 | -17
| Estimated Remaining Hours | 124 | 115.1429 | 106.2857 | 97.4286 | 88.5714 | 79.7143 | 70.8571 | 62 | 53.1429 | 44.2857 | 35.4286 | 26.5714 | 17.7143 | 8.8571 | -4.2633e-14