## Sheet1
USER STORY | TASKS | Start Time | Sprint no.3 Backlog | [13 empty] | Total Time
|  |  | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
As a user I should be able to view the weather of any location | Create component | 6 | Sprint no.3 Backlog Day 1: 3; Sprint no.3 Backlog Day 2: 1; Sprint no.3 Backlog Day 3: 2; Sprint no.3 Backlog Day 4: 1 | 7
| Create disaster service | 20 |  |  |  | 3 | 5 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 24
| Add mock objects | 5 | Sprint no.3 Backlog Day 7: 2; Sprint no.3 Backlog Day 8: 2; Sprint no.3 Backlog Day 10: 1; Sprint no.3 Backlog Day 11: 1 | 6
| Display information on map component | 20 | Sprint no.3 Backlog Day 9: 5; Sprint no.3 Backlog Day 10: 3; Sprint no.3 Backlog Day 11: 3; Sprint no.3 Backlog Day 12: 4; Sprint no.3 Backlog Day 13: 2; Sprint no.3 Backlog Day 14: 1 | 18
| Create disaster interface | 1 | Sprint no.3 Backlog Day 6: 2 | 2
0
0
As a user I should be able to view disasters for any location | Create disaster service | 4 | Sprint no.3 Backlog Day 1: 2; Sprint no.3 Backlog Day 2: 3 | 5
| Integrated with back-end server | 2 | [14 empty] | 2 | bar: Sprint no.3 Backlog Day 3 to Sprint no.3 Backlog Day 4
| Visualize earthquake data using map service | 24 | Sprint no.3 Backlog Day 5: 5; Sprint no.3 Backlog Day 6: 6; Sprint no.3 Backlog Day 7: 5; Sprint no.3 Backlog Day 8: 6; Sprint no.3 Backlog Day 9: 5 | 27
| Visualize fire data using map service | 2 | Sprint no.3 Backlog Day 10: 2 | 2
| Impelemented data clustering | 20 | Sprint no.3 Backlog Day 11: 5; Sprint no.3 Backlog Day 12: 7; Sprint no.3 Backlog Day 13: 6; Sprint no.3 Backlog Day 14: 4 | 22
| Implemeted time series query | 3 | Sprint no.3 Backlog Day 10: 4 | 4
0
| Actual Remaining Hours | 107 | 102 | 98 | 95 | 90 | 80 | 72 | 63 | 53 | 41 | 29 | 18 | 5 | -5 | -12
| Estimated Remaining Hours | 107 | 99.3571 | 91.7143 | 84.0714 | 76.4286 | 68.7857 | 61.1429 | 53.5 | 45.8571 | 38.2143 | 30.5714 | 22.9286 | 15.2857 | 7.6429 | 8.8818e-15